## Estimate Summary
Estimation Summary
Project Information
Start Date | 2019-01-01
Resources | 4
Effort
Person*Days | 169.625
Duration
Estimated Duration | 42.4062
Availability Buffer | 4.5435
Estimated End Date | 2019-03-06
Initial Cost
Initiation Cost | 206320
Effort Expense
Role | Hours | Rate | Total
BA | 553 | 150 | 82950
Dev | 920.8 | 150 | 138120
User | 531.2 | 180 | 95616
316686
Oversight Expense
Arch | 339.25 | 150 | 50887.5
PM | 339.25 | 150 | 50887.5
101775
Post-Live Support
Role | Hours | Rate | Total
Dev | 320 | 150 | 48000
BA | 320 | 150 | 48000
96000
Risk Factor
|  | low | high
Risk % | 25% | -52307.625 | 52307.625
Contigency | 10% | 41846.1
Availability | 89.29% | 44835.1071
Total Cost
| low | high
Project Cost Range | 755154.5821 | 859769.8321

## Initiation Costs
ID | Item | Project Team Effort | Shared Service Effort | User Effort | Production License | Test License | Development License | Disaster Recovery | Total
1 | Visualization
1.1 | Technology selection | 5 | 5 | 3
1.2 | Licensing |  |  |  | 1000 | 0 | 0 | 1000
1.3 | Platform development | 10
1.4 | Server allocation |  | 10 |  | 10000 | 1000 | 1000 | 10000
1.5 | Installation |  | 5
2 | Storage
2.1 | Technology selection | 5
2.2 | Licensing |  |  |  | 50000 | 0 | 0 | 50000
2.3 | Server Allocation |  | 10
2.4 | Installation |  | 5
3 | ETL
3.1 | Technology selection | 0
3.2 | Licensing |  |  |  | 0 | 0 | 0 | 0
3.3 | Installation
4 | Scheduling/Triggering
4.1 | Technology selection | 5 | 5 |  | 0 | 0 | 0 | 0
|  | 25 | 40 | 3 | 61000 | 1000 | 1000 | 61000
| Rate | 150 | 150 | 180
| Total | 30000 | 48000 | 4320 | 61000 | 1000 | 1000 | 61000 | 206320

## Component Types
| Effort |  |  | Life_Cycle Allocations
Component Type | 01-Low | 02-Med | 03-High | 01-Rqmts | 02-Design | 03-Dev | 04-Test
ETL | 2.125 | 4.25 | 8.5 | 10% | 25% | 100% | 35%
Scheduling/Triggering | 1.125 | 2.25 | 4.5 | 10% | 10% | 100% | 10%
Storage | 1.25 | 2.5 | 5 | 10% | 10% | 100% | 10%
Visualization | 1 | 2 | 4 | 25% | 10% | 100% | 35%

## Doneness Steps
Component Type | Doneness Step | 01-Low | 02-Med | 03-High
Visualization | a. Query – write a query against the ODS | 0.375 | 0.75 | 1.5
Visualization | b. Filter – provide a way to narrow the results | 0.5 | 1 | 2
Visualization | c. Presentation – present the information according to the requirements | 0.125 | 0.25 | 0.5
Storage | a. Table – data structure to hold the report | 0.5 | 1 | 2
Storage | b. Indexes – indexes needed for efficient presentation | 0.5 | 1 | 2
Storage | c. Partitioning – structure for efficient storage and retrieval | 0.25 | 0.5 | 1
ETL | a. Source Extraction Query – write a query against the source system | 0.25 | 0.5 | 1
ETL | b. Transformation – resolve foreign key references and denormalize as needed | 0.125 | 0.25 | 0.5
ETL | c. Insert – insert into the storage table | 0.5 | 1 | 2
ETL | d. Error Handling – account for possible problems | 0.625 | 1.25 | 2.5
ETL | e. Reconciliation – provide a mechanism to ensure data quality | 0.625 | 1.25 | 2.5
Scheduling/Triggering | a. Control Integration – call the custom code from the scheduling service | 0.5 | 1 | 2
Scheduling/Triggering | b. Error Handling – detect errors in the custom code | 0.5 | 1 | 2
Scheduling/Triggering | c. Notification – notify administrators when problems occur | 0.125 | 0.25 | 0.5

## Effort
ID | Level | Item | Functional Area | Component Type | Complexity | Life-Cycle | Iteration | Duration | BA | Dev | User | Total Effort
1 | 1 | Orders |  |  |  |  | Iteration 1
1.1 | 2 | Visualization | Orders |  |  |  | Iteration 1
1.1.1 | 3 | 01-Rqmts | Orders | Visualization | 03-High | 01-Rqmts | Iteration 1 | 1 | 1 | 0.25 | 1 | 2.25
1.1.2 | 3 | 02-Design | Orders | Visualization | 03-High | 02-Design | Iteration 1 | 0.4 | 0.1 | 0.4 | 0 | 0.5
1.1.3 | 3 | 03-Dev | Orders | Visualization | 03-High | 03-Dev | Iteration 1 | 4 | 1 | 4 | 1 | 6
1.1.4 | 3 | 04-Test | Orders | Visualization | 03-High | 04-Test | Iteration 1 | 1.4 | 1.4 | 1.4 | 1.4 | 4.2
1.2 | 2 | Storage | Orders |  |  |  | Iteration 1
1.2.1 | 3 | 01-Rqmts | Orders | Storage | 02-Med | 01-Rqmts | Iteration 1 | 0.25 | 0.25 | 0.0625 | 0.25 | 0.5625
1.2.2 | 3 | 02-Design | Orders | Storage | 02-Med | 02-Design | Iteration 1 | 0.25 | 0.0625 | 0.25 | 0 | 0.3125
1.2.3 | 3 | 03-Dev | Orders | Storage | 02-Med | 03-Dev | Iteration 1 | 2.5 | 0.625 | 2.5 | 0.625 | 3.75
1.2.4 | 3 | 04-Test | Orders | Storage | 02-Med | 04-Test | Iteration 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.75
1.3 | 2 | ETL | Orders |  |  |  | Iteration 1
1.3.1 | 3 | 01-Rqmts | Orders | ETL | 03-High | 01-Rqmts | Iteration 1 | 0.85 | 0.85 | 0.2125 | 0.85 | 1.9125
1.3.2 | 3 | 02-Design | Orders | ETL | 03-High | 02-Design | Iteration 1 | 2.125 | 0.53125 | 2.125 | 0 | 2.6562
1.3.3 | 3 | 03-Dev | Orders | ETL | 03-High | 03-Dev | Iteration 1 | 8.5 | 2.125 | 8.5 | 2.125 | 12.75
1.3.4 | 3 | 04-Test | Orders | ETL | 03-High | 04-Test | Iteration 1 | 2.975 | 2.975 | 2.975 | 2.975 | 8.925
1.4 | 2 | Scheduling/Triggering | Orders |  |  |  | Iteration 1
1.4.1 | 3 | 01-Rqmts | Orders | Scheduling/Triggering | 01-Low | 01-Rqmts | Iteration 1 | 0.1125 | 0.1125 | 0.028125 | 0.1125 | 0.25312
1.4.2 | 3 | 02-Design | Orders | Scheduling/Triggering | 01-Low | 02-Design | Iteration 1 | 0.1125 | 0.028125 | 0.1125 | 0 | 0.14062
1.4.3 | 3 | 03-Dev | Orders | Scheduling/Triggering | 01-Low | 03-Dev | Iteration 1 | 1.125 | 0.28125 | 1.125 | 0.28125 | 1.6875
1.4.4 | 3 | 04-Test | Orders | Scheduling/Triggering | 01-Low | 04-Test | Iteration 1 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.3375
2 | 1 | Sales |  |  |  |  | Iteration 2
2.1 | 2 | Visualization | Sales |  |  |  | Iteration 2
2.1.1 | 3 | 01-Rqmts | Sales | Visualization | 02-Med | 01-Rqmts | Iteration 2 | 0.5 | 0.5 | 0.125 | 0.5 | 1.125
2.1.2 | 3 | 02-Design | Sales | Visualization | 02-Med | 02-Design | Iteration 2 | 0.2 | 0.05 | 0.2 | 0 | 0.25
2.1.3 | 3 | 03-Dev | Sales | Visualization | 02-Med | 03-Dev | Iteration 2 | 2 | 0.5 | 2 | 0.5 | 3
2.1.4 | 3 | 04-Test | Sales | Visualization | 02-Med | 04-Test | Iteration 2 | 0.7 | 0.7 | 0.7 | 0.7 | 2.1
2.2 | 2 | Storage | Sales |  |  |  | Iteration 2
2.2.1 | 3 | 01-Rqmts | Sales | Storage | 01-Low | 01-Rqmts | Iteration 2 | 0.125 | 0.125 | 0.03125 | 0.125 | 0.28125
2.2.2 | 3 | 02-Design | Sales | Storage | 01-Low | 02-Design | Iteration 2 | 0.125 | 0.03125 | 0.125 | 0 | 0.15625
2.2.3 | 3 | 03-Dev | Sales | Storage | 01-Low | 03-Dev | Iteration 2 | 1.25 | 0.3125 | 1.25 | 0.3125 | 1.875
2.2.4 | 3 | 04-Test | Sales | Storage | 01-Low | 04-Test | Iteration 2 | 0.125 | 0.125 | 0.125 | 0.125 | 0.375
2.3 | 2 | ETL | Sales |  |  |  | Iteration 2
2.3.1 | 3 | 01-Rqmts | Sales | ETL | 03-High | 01-Rqmts | Iteration 2 | 0.85 | 0.85 | 0.2125 | 0.85 | 1.9125
2.3.2 | 3 | 02-Design | Sales | ETL | 03-High | 02-Design | Iteration 2 | 2.125 | 0.53125 | 2.125 | 0 | 2.6562
2.3.3 | 3 | 03-Dev | Sales | ETL | 03-High | 03-Dev | Iteration 2 | 8.5 | 2.125 | 8.5 | 2.125 | 12.75
2.3.4 | 3 | 04-Test | Sales | ETL | 03-High | 04-Test | Iteration 2 | 2.975 | 2.975 | 2.975 | 2.975 | 8.925
2.4 | 2 | Scheduling/Triggering | Sales |  |  |  | Iteration 2
2.4.1 | 3 | 01-Rqmts | Sales | Scheduling/Triggering | 01-Low | 01-Rqmts | Iteration 2 | 0.1125 | 0.1125 | 0.028125 | 0.1125 | 0.25312
2.4.2 | 3 | 02-Design | Sales | Scheduling/Triggering | 01-Low | 02-Design | Iteration 2 | 0.1125 | 0.028125 | 0.1125 | 0 | 0.14062
2.4.3 | 3 | 03-Dev | Sales | Scheduling/Triggering | 01-Low | 03-Dev | Iteration 2 | 1.125 | 0.28125 | 1.125 | 0.28125 | 1.6875
2.4.4 | 3 | 04-Test | Sales | Scheduling/Triggering | 01-Low | 04-Test | Iteration 2 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.3375
3 | 1 | Purchases |  |  |  |  | Iteration 3
3.1 | 2 | Visualization | Purchases |  |  |  | Iteration 3
3.1.1 | 3 | 01-Rqmts | Purchases | Visualization | 03-High | 01-Rqmts | Iteration 3 | 1 | 1 | 0.25 | 1 | 2.25
3.1.2 | 3 | 02-Design | Purchases | Visualization | 03-High | 02-Design | Iteration 3 | 0.4 | 0.1 | 0.4 | 0 | 0.5
3.1.3 | 3 | 03-Dev | Purchases | Visualization | 03-High | 03-Dev | Iteration 3 | 4 | 1 | 4 | 1 | 6
3.1.4 | 3 | 04-Test | Purchases | Visualization | 03-High | 04-Test | Iteration 3 | 1.4 | 1.4 | 1.4 | 1.4 | 4.2
3.2 | 2 | Storage | Purchases |  |  |  | Iteration 3
3.2.1 | 3 | 01-Rqmts | Purchases | Storage | 02-Med | 01-Rqmts | Iteration 3 | 0.25 | 0.25 | 0.0625 | 0.25 | 0.5625
3.2.2 | 3 | 02-Design | Purchases | Storage | 02-Med | 02-Design | Iteration 3 | 0.25 | 0.0625 | 0.25 | 0 | 0.3125
3.2.3 | 3 | 03-Dev | Purchases | Storage | 02-Med | 03-Dev | Iteration 3 | 2.5 | 0.625 | 2.5 | 0.625 | 3.75
3.2.4 | 3 | 04-Test | Purchases | Storage | 02-Med | 04-Test | Iteration 3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.75
3.3 | 2 | ETL | Purchases |  |  |  | Iteration 3
3.3.1 | 3 | 01-Rqmts | Purchases | ETL | 03-High | 01-Rqmts | Iteration 3 | 0.85 | 0.85 | 0.2125 | 0.85 | 1.9125
3.3.2 | 3 | 02-Design | Purchases | ETL | 03-High | 02-Design | Iteration 3 | 2.125 | 0.53125 | 2.125 | 0 | 2.6562
3.3.3 | 3 | 03-Dev | Purchases | ETL | 03-High | 03-Dev | Iteration 3 | 8.5 | 2.125 | 8.5 | 2.125 | 12.75
3.3.4 | 3 | 04-Test | Purchases | ETL | 03-High | 04-Test | Iteration 3 | 2.975 | 2.975 | 2.975 | 2.975 | 8.925
3.4 | 2 | Scheduling/Triggering | Purchases |  |  |  | Iteration 3
3.4.1 | 3 | 01-Rqmts | Purchases | Scheduling/Triggering | 01-Low | 01-Rqmts | Iteration 3 | 0.1125 | 0.1125 | 0.028125 | 0.1125 | 0.25312
3.4.2 | 3 | 02-Design | Purchases | Scheduling/Triggering | 01-Low | 02-Design | Iteration 3 | 0.1125 | 0.028125 | 0.1125 | 0 | 0.14062
3.4.3 | 3 | 03-Dev | Purchases | Scheduling/Triggering | 01-Low | 03-Dev | Iteration 3 | 1.125 | 0.28125 | 1.125 | 0.28125 | 1.6875
3.4.4 | 3 | 04-Test | Purchases | Scheduling/Triggering | 01-Low | 04-Test | Iteration 3 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.3375
4 | 1 | Inventory |  |  |  |  | Iteration 4
4.1 | 2 | Visualization | Inventory |  |  |  | Iteration 4
4.1.1 | 3 | 01-Rqmts | Inventory | Visualization | 02-Med | 01-Rqmts | Iteration 4 | 0.5 | 0.5 | 0.125 | 0.5 | 1.125
4.1.2 | 3 | 02-Design | Inventory | Visualization | 02-Med | 02-Design | Iteration 4 | 0.2 | 0.05 | 0.2 | 0 | 0.25
4.1.3 | 3 | 03-Dev | Inventory | Visualization | 02-Med | 03-Dev | Iteration 4 | 2 | 0.5 | 2 | 0.5 | 3
4.1.4 | 3 | 04-Test | Inventory | Visualization | 02-Med | 04-Test | Iteration 4 | 0.7 | 0.7 | 0.7 | 0.7 | 2.1
4.2 | 2 | Storage | Inventory |  |  |  | Iteration 4
4.2.1 | 3 | 01-Rqmts | Inventory | Storage | 01-Low | 01-Rqmts | Iteration 4 | 0.125 | 0.125 | 0.03125 | 0.125 | 0.28125
4.2.2 | 3 | 02-Design | Inventory | Storage | 01-Low | 02-Design | Iteration 4 | 0.125 | 0.03125 | 0.125 | 0 | 0.15625
4.2.3 | 3 | 03-Dev | Inventory | Storage | 01-Low | 03-Dev | Iteration 4 | 1.25 | 0.3125 | 1.25 | 0.3125 | 1.875
4.2.4 | 3 | 04-Test | Inventory | Storage | 01-Low | 04-Test | Iteration 4 | 0.125 | 0.125 | 0.125 | 0.125 | 0.375
4.3 | 2 | ETL | Inventory |  |  |  | Iteration 4
4.3.1 | 3 | 01-Rqmts | Inventory | ETL | 03-High | 01-Rqmts | Iteration 4 | 0.85 | 0.85 | 0.2125 | 0.85 | 1.9125
4.3.2 | 3 | 02-Design | Inventory | ETL | 03-High | 02-Design | Iteration 4 | 2.125 | 0.53125 | 2.125 | 0 | 2.6562
4.3.3 | 3 | 03-Dev | Inventory | ETL | 03-High | 03-Dev | Iteration 4 | 8.5 | 2.125 | 8.5 | 2.125 | 12.75
4.3.4 | 3 | 04-Test | Inventory | ETL | 03-High | 04-Test | Iteration 4 | 2.975 | 2.975 | 2.975 | 2.975 | 8.925
4.4 | 2 | Scheduling/Triggering | Inventory |  |  |  | Iteration 4
4.4.1 | 3 | 01-Rqmts | Inventory | Scheduling/Triggering | 01-Low | 01-Rqmts | Iteration 4 | 0.1125 | 0.1125 | 0.028125 | 0.1125 | 0.25312
4.4.2 | 3 | 02-Design | Inventory | Scheduling/Triggering | 01-Low | 02-Design | Iteration 4 | 0.1125 | 0.028125 | 0.1125 | 0 | 0.14062
4.4.3 | 3 | 03-Dev | Inventory | Scheduling/Triggering | 01-Low | 03-Dev | Iteration 4 | 1.125 | 0.28125 | 1.125 | 0.28125 | 1.6875
4.4.4 | 3 | 04-Test | Inventory | Scheduling/Triggering | 01-Low | 04-Test | Iteration 4 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.3375

## Timeline (Agile)
Interval | 1 | day
Resources | 4 | people
Level | 3
[6 empty] | 2019-01-01 | [22 empty] | 2019-02-01 | [19 empty] | 2019-03-01 | [20 empty] | 2019-04-01 | [20 empty] | 2019-05-01 | [21 empty] | 2019-06-03 | [19 empty] | 2019-07-01 | [22 empty] | 2019-08-01 | [21 empty] | 2019-09-02
Row Labels | Sum of Total Effort |  | Duration | Start | Finish | time axis 2019-01-01 to 2019-09-20
Iteration 1 | 46.9875 |  | 11.7469 | 2019-01-01 | 2019-01-16 | 2019-01-01: 11.7469; 2019-01-02: 11.7469; 2019-01-03: 11.7469; 2019-01-04: 11.7469; 2019-01-07: 11.7469; 2019-01-08: 11.7469; 2019-01-09: 11.7469; 2019-01-10: 11.7469; 2019-01-11: 11.7469; 2019-01-14: 11.7469; 2019-01-15: 11.7469
Iteration 2 | 37.825 |  | 9.4562 | 2019-01-16 | 2019-01-29 | 2019-01-16: 9.4562; 2019-01-17: 9.4562; 2019-01-18: 9.4562; 2019-01-21: 9.4562; 2019-01-22: 9.4562; 2019-01-23: 9.4562; 2019-01-24: 9.4562; 2019-01-25: 9.4562; 2019-01-28: 9.4562
Iteration 3 | 46.9875 |  | 11.7469 | 2019-01-29 | 2019-02-13 | 2019-01-29: 11.7469; 2019-01-30: 11.7469; 2019-01-31: 11.7469; 2019-02-01: 11.7469; 2019-02-04: 11.7469; 2019-02-05: 11.7469; 2019-02-06: 11.7469; 2019-02-07: 11.7469; 2019-02-08: 11.7469; 2019-02-11: 11.7469; 2019-02-12: 11.7469
Iteration 4 | 37.825 |  | 9.4563 | 2019-02-13 | 2019-02-26 | 2019-02-13: 9.4563; 2019-02-14: 9.4563; 2019-02-15: 9.4563; 2019-02-18: 9.4563; 2019-02-19: 9.4563; 2019-02-20: 9.4563; 2019-02-21: 9.4563; 2019-02-22: 9.4563; 2019-02-25: 9.4563
Grand Total | 169.625 |  | 42.4062

## Timeline (Waterfall)
Interval | 5 | days
Resources | 4 | people
Level | 3
[6 empty] | 2019-01-01 |  |  |  |  | 2019-02-05 |  |  |  | 2019-03-05 |  |  |  | 2019-04-02 |  |  |  | 2019-05-01 |  |  |  |  | 2019-06-06 |  |  |  | 2019-07-04 |  |  |  | 2019-08-01 |  |  |  |  | 2019-09-05 |  |  |  | 2019-10-03 |  |  |  |  | 2019-11-07 |  |  |  | 2019-12-05 |  |  |  | 2020-01-02 |  |  |  |  | 2020-02-06 |  |  |  | 2020-03-05 |  |  |  | 2020-04-02 |  |  |  |  | 2020-05-07 |  |  |  | 2020-06-04 |  |  |  | 2020-07-02 |  |  |  |  | 2020-08-06 |  |  |  | 2020-09-03 |  |  |  | 2020-10-01 |  |  |  |  | 2020-11-05 |  |  |  | 2020-12-03 |  |  |  |  | 2021-01-07 |  |  |  | 2021-02-04 |  |  |  | 2021-03-04 |  |  |  | 2021-04-01 |  |  |  |  | 2021-05-06 |  |  |  | 2021-06-03 |  |  |  | 2021-07-01 |  |  |  |  | 2021-08-05 |  |  |  | 2021-09-02 |  |  |  |  | 2021-10-07 |  |  |  | 2021-11-04 |  |  |  | 2021-12-02 |  |  |  |  | 2022-01-06 |  |  |  | 2022-02-03 |  |  |  | 2022-03-03 |  |  |  |  | 2022-04-07 |  |  |  | 2022-05-05 |  |  |  | 2022-06-02 |  |  |  |  | 2022-07-07
Row Labels | Sum of Duration |  | Duration | Start | Finish | time axis 2019-01-01 to 2022-07-28
01-Rqmts | 7.6 |  | 1.9 | 2019-01-01 | 2019-01-10 | 2019-01-01: 1.9; 2019-01-08: 1.9
02-Design | 10.9 |  | 2.725 | 2019-01-10 | 2019-01-24 | 2019-01-15: 2.725; 2019-01-22: 2.725
03-Dev | 58 |  | 14.5 | 2019-01-24 | 2019-04-16 | 2019-01-29: 14.5; 2019-02-05: 14.5; 2019-02-12: 14.5; 2019-02-19: 14.5; 2019-02-26: 14.5; 2019-03-05: 14.5; 2019-03-12: 14.5; 2019-03-19: 14.5; 2019-03-26: 14.5; 2019-04-02: 14.5; 2019-04-09: 14.5
04-Test | 17.3 |  | 4.325 | 2019-04-16 | 2019-05-10 | 2019-04-16: 4.325; 2019-04-24: 4.325; 2019-05-01: 4.325; 2019-05-08: 4.325
Grand Total | 93.8 |  | 23.45

## Rates
Role | Rate $/Hr | Hrs/Day | US Holidays
Arch | 150 | 8 | New Year's Day | 2019-01-01
BA | 150 |  | Good Friday | 2019-04-19
Dev | 150 |  | Memorial Day | 2019-05-27
PM | 150
User | 180

## Availability
Category | Per-Person Annual Policy
Vacation | 15
Sick Days | 10
Personal Time Off | 2
Total | 27

## Roles
Role | 01-Rqmts | 02-Design | 03-Dev | 04-Test
BA | 100% | 25% | 25% | 100%
Dev | 25% | 100% | 100% | 100%
User | 100% | 0% | 25% | 100%

## Risks
ID | Risk | Yes | No | Response | Risk Factor | Risk Spread
1 | Does the team understand the domain? | the team knows the business | the team is not familiar with the business | N | 5% | 5%
2 | Is the team familiar with the tools and technology? | team has experience with the tools and technology | the team has not used the tools or the technology in the past | N | 5% | 5%
3 | Are the requirements stable? | the business requirements are stable and not likely to change significantly | the organization is still figuring things out | N | 5% | 5%
4 | Is the solution well-understood? | the architect, team, and business users understand the solution and are in agreement | the solution is in flux, for any reason | N | 5% | 5%
5 | Are the stakeholders available to support the project? | there is a clear mandate for the project and the stakeholders agree with the direction | there is disagreement among the stakeholders concerning project direction | N | 5% | 5%
25%

## Assumptions
ID | Assumption
1 | A staff is available at the start of the project

## Illustration (hidden)
|  |  | Month 1 | Month 2 | Month 3 | Month 4
|  | Person 1 | 4 people for 4 months Effort = 16 person*months
Person 2
Person 3
Person 4
has the same effort as
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8
Person 1 | Month 1: 2 people for 8 months Effort = 16 person*months
Person 2